## Sheet1
LIFT EXPENSES AND ACTIONS -5/14/16 | [5 empty] | Paid vs. Unpaid Detail
as of 2/25/16
Phase I – Work Required: |  |  |  |  | Notes | paid | not yet paid | Payment details
1 | Sitework for Lift
2 |  | Tree Removal | 2000 |  |  | 2000 |  | 9/30/15 Bartlett
3 |  | Concrete Foundation | 8000 |  |  |  | 8000 |  | 3 quotes on vendors needed
4 |  | Dig Trench/Move Electric | 3000 |  |  |  | 3000 |  | 2 quotes on vendors needed-batch?
5 |  | Demolition Water Chamber | Excluded |  | Existing pump box appears active.
6 |  | Grade Lift Area | 2500 |  |  |  | 2500 |  | 2 quotes on vendors needed-batch?
7 |  | Relocations & Misc Work | 2000 |  |  |  | 2000 |  | 2 quotes on vendors needed-batch?
8
9 | Early Work
10 |  | Oil Tank Removal, Lift Deposit & (Professional Fees to Land Use Constnt) | 18500 |  | Work Complete. Previously Spent. | 17100 |  | 1/31/14 $15K Lift deposit, 3/6/14 $200 rendering, 5/9 and 5/27/14 $1,900 oil tank removal
11
12 | Consultants
13 |  | Land Use Consultants | 10000 |  | Original estimate increased by P&Z delays | 11107 |  | Pmts made 8/20/14, 12/17/14, 6/17/15, 7/8/15,8/14/15
14 |  | Barr Associates | 4000 | #2 | Text Amendment & Lift DOB Filings | 2267 | 1733 | Pmts made 10/13/15, 2/11/16 | underway
15 |  | Wetlands Mapping | 800 |  | Landtech | 750 |  |  | no 3 quote
16 |  | Leonard Surveying | 4000 |  |  | 5048 |  | Pmts made 1/14/16, 1/31/16 | no 3 quote
17 |  | Architect | 3500 |  |  | 3500 |  | Pmts made 8/20/14, 10/21/15 | orig contract was $3500 not $2500- so error in compiling sheet; final amount paid Mar.2016
18 |  | Town Fees & Applications | 2000 | #3 |  | 1285 | 700 | text amend fee pd 11/10/15 | guess at additional fees
19 | Total |  | 60300 |  |  | 43057 | 17933
Phase II - Final Phase: |  |  |  |  | Notes
1 | Lift Installation
2 |  | Delivery & Install Lift | 16206 | #4 | Deposit for Lift paid previously. |  | 16206 |  | updated quote from Freedom Lifts 3May 2016, most due upon delivery, remainder upon completion
3 |  | Paving & walkways | 10000 |  |  |  | 10000
4 |  | Electric door installed | 2000 |  |  |  | 2000
5 | Total |  | 28206
| Total Cost Estimate |  | 88506 | #5 |  | 43057 | 46139 | 89196
[6 empty] | Excess over estimate |  | 690
Notes:
1 | Completion date anticipated end of 9/16. Original completion date changed due to P&Z delay.
2 | Barr Associates should be $1,000 under budget.
3 | Fees & Applications will increase…Amount not known.
4 | Lift increase of $ 1,652 due to P&Z delay.
5 | Significant increase in budget is not anticipated.
TIME LINE
1 | All Westport Departments, prior to applying for a building permit have approved building plans.
2 | 5/20: Preliminary meeting with the Director of Building Dept. (Steve Smith) to start the approval process of the lift drawings.
3 | 5/23: Two General contractors will be requested to bid. A. Pappajohn Co. Con. and Michael Zeoli Building. We are currently
researcging a third bidder.
4 | 6/10: TUCW complete Contractor approval(s) and sign contract(s).
5 | 6/15-7/31 Pre installation work: Excavation, Formwork, Rough Grading, Concrete Foundation, Trenching & Electric Connection.
6 | 7/25 - 8/26 Lift Installation. Structural Connection, Railings, Power & Lighting. Finish Grading & Sitework, Asphalt Paving & repair.
7 | 9/23: Line striping, finish sitework, complete punch list and paperwork.

## Spending Summary
Lift Spending Summary
Expense Summary by Fiscal Year
Spent in Fiscal 2015 | 23069
Spent thru 3/3/1/16 in Fiscal 2016 | 19988
Expected Spending 3/31/16 - 6/30/16 | 26443
Total Expected Spending Thru 6/30/16 (FY16) | 69500
Remainder to be Spent in FY17 | 23500
Total Lift Budget | 93000
Sources of Funding
Donations | 43500
Operating Budget | 49500
Total Lift Funding | 93000